## Agile Product Backlog
SPRINT # | TASK | TASK NAME | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | REVIEW BY AMIT
Sprint 1 |  |  | Kavya |  |  | High | In Progress
| LOGIN COMPONENT | Static HTML page design | " " |  |  | Medium | Complete | OK
|  | Adding CSS to page | " " |  |  | Medium | Complete | OK
|  | Making page Responsive | " " |  |  | Medium | In-progress | Page should be mobile friendly
|  | Convert HTML page into react component | " " |  |  | Medium
|  | Create API clients for Microservices | " " |  |  | Medium
|  | Handling the json objects | " " |  |  | Medium
|  | Data binding with front end and client | " " |  |  | Medium
|  |  | Sneha |  |  | High | In Progress
| ROLE MANAGEMENT COMPONENT | Static HTML page design | " " |  |  | Medium | Complete | OK
|  | Adding CSS to page | " " |  |  | Medium | Complete | OK
|  | Making page Responsive | " " |  |  | Medium | In-progress | Overlapping elements should be avoided
|  | Convert HTML page into react component | " " |  |  | Medium
|  | Create API clients for Microservices | " " |  |  | Medium
|  | Handling the json objects | " " |  |  | Medium
|  | Data binding with front end and client | " " |  |  | Medium
|  |  | Bindu Shree |  |  | High | In Progress | In Progress
| USER MANAGEMENT COMPONENT | Static HTML page design | " " |  |  | Medium | Complete | OK
|  | Adding CSS to page | " " |  |  | Medium | Complete | OK
|  | Making page Responsive | " " |  |  | Medium | In-progess
|  | Convert HTML page into react component | " " |  |  | Medium
|  | Create API clients for Microservices | " " |  |  | Medium
|  | Handling the json objects | " " |  |  | Medium
|  | Data binding with front end and client | " " |  |  | Medium